## Project_Scope
NCD ISSUANCE TRACKER - PROJECT SCOPE
PROJECT NAME | NCD Issuance Tracker
CONTEXT | Structured Product Solutions — Issuer Readiness
OBJECTIVE | End-to-end tracking of Non-Convertible Debenture (NCD) issuances from pipeline initiation through pre-execution, documentation, T-Day, and post-issuance. Replace Google Sheets workflow with purpose-built web application.
PRIMARY USERS | Internal deal team (Structured Products / Bond Primary Deals desk)
INSTRUMENT TYPES | Listed NCD, Unlisted NCD
ISSUER CLASSIFICATION | FS (Financial Sector/NBFC) ¦ EF (Enterprise Finance/Corporate)
KEY DELIVERABLES
1. Web Application | • User-friendly dashboard for managing NCD issuances • Issuance cards showing status, progress, T-countdown • Filter by Listed/Unlisted
2. Workflow Management | • 5-phase checklist: Pre-Execution → Depository & Stamping → Documents & EBP → T-Day → Post-Issuance • Role tracking (Maker attribution per task) • Progress tracking with completion %
3. Document Management | • Auto-populate term sheets from deal initiation data • Highlight fields requiring manual input • Secure local storage (Phase 1: E:\ drive) and files to be stored in 'E:\Personal\Trading_Champion\Projects\Solutions_Execution\Issuance'
4. Data Management | • Excel-based storage (Bond_Primary_Deals.xlsx) • Pipeline Issuance sheet (active deals) • Closed NCD Deal sheet (archived deals)
DEPLOYMENT
Platform | Streamlit web application
Storage (Phase 1) | Local file system: E:\Personal\Trading_Champion\Projects\Solutions_Execution
Authentication (Phase 1) | None - Open access (single user/trusted team)
Database (Phase 1) | Excel-based (Bond_Primary_Deals.xlsx)
SUCCESS METRICS
• Reduction in processing time for NCD issuances
• Improved tracking and compliance rates
• User satisfaction post-implementation
FUTURE SCOPE (Phase 2)
• Google Drive API integration
• User authentication & role-based access (Maker/Checker/Admin)
• Email/Slack notifications
• Term sheet comparison tool (AI-powered)
• ISIN auto-tracking with NSDL/CDSL

## Screens_Navigation
SCREENS & NAVIGATION STRUCTURE
Screen No. | Screen Name | Description | Access Type
1A | Dashboard / Home | Shows all active issuances as cards with summary stats at top (Total Issuances, Fully Funded, In Progress, Due ≤7 Days). Filter bar (All / Listed NCD / Unlisted NCD). "+ New Issuance" button. | Read + Write
1B | Issuance Pipeline (List View) | Alternative view: list of issuances sourced from Issuance Pipeline sheet. Can be toggled from left panel or top tab. | Read Only
2 | New Deal Initiation | Form triggered by "+ New Issuance" button. Captures: Issuer name, Issuer type (FS/EF), Listed/Unlisted, Quantum (Rs. Cr), Tentative T-date, Asset Class. Generates basic Term Sheet stub. Writes to Pipeline. | Write
3 | Deal Detail / Checklist View | Per-issuance screen (e.g., "Acme Finance Ltd"). Shows 5 phase tabs (Pre-Exec, Depo & Stamp, Docs & EBP, T-Day, Post). Each phase has numbered checklist items with status (Pending/Done), Maker attribution, sub-notes. | Read + Write
4 | Closed Deals View | Once deal marked closed, moves from Pipeline to Closed NCD Deal sheet/view. Captures: ISIN, Coupon, Tenor, Rating, Maturity, etc. | Read + Archive

## Dashboard_Cards
DASHBOARD COMPONENTS
SUMMARY STATS BAR
Metric | Logic | Visual Treatment
Total Issuances | Count of all active deals in the pipeline | Large number, neutral color
Fully Funded | Deals where all checklist steps = complete AND funding confirmed | Green accent
In Progress | Deals with partial checklist completion | Yellow/amber accent
Due ≤7 Days | Deals where T-date minus today ≤ 7 calendar days | Red/alert accent
ISSUANCE CARD (Dashboard View)
Field | Source / Logic | Notes
Issuer Name | Entered at deal initiation | Primary identifier
Instrument Badge | Listed NCD / Unlisted NCD | Color-coded badge
Quantum | e.g., Rs. 50 Cr | From initiation form
T-Date | Funding Date (absolute date, e.g., 2026-03-28) | Calendar date
T-Countdown | Days remaining to T-date (e.g., T-14d) | Red if ≤7d, Yellow if 8–21d, Green if >21d
Pre-funding Progress | X / Total Steps · % complete (e.g., 0/37 · 0%) | Overall progress bar
Phase Mini-Progress | Icons + step counts for: Pre-Exec, Depo & Stamp, Docs & EBP, T-Day, Post | Quick visual status

## Checklist_Structure
CHECKLIST STRUCTURE & PHASES
PHASE TAB STRUCTURE
Tab Name | Example Steps (User to provide compressed 3-5 key items per phase)
Pre-Execution Setup | • Final Term Sheet (Yubi & Issuer) • Board Resolution - authorizing the issue (Issuer) • Shareholder Resolution - Sec 180 + Form MGT-14 (Issuer) • Costing sheet in place [User to provide complete 3-5 items]
Depository & Stamping | • NSDL and CDSL Agreements (Issuer) • Stamp duty payment confirmation (Issuer) • Scores Regn & In principle approgal form BSE (only for Listed issuance) [User to provide complete 3-5 items]
Documents & EBP | • DTD, DTA and DOH executed (Trustee) • GID and KID (For listed issuance) • Private Placement Offer Letter (Form PAS 4) (Legal Counsel) [User to provide complete 3-5 items]
T-Day (Funding Day) | • Pay-in / Funding received and confirmed (Yubi) • Demat credit to investors (Registrar) [User to provide complete 3-5 items]
Post-Issuance | • Form PAS-3 filed with ROC (Issuer) • BSE listing confirmation (if Listed) (Issuer) [User to provide complete 3-5 items]
CHECKLIST ITEM STRUCTURE (Per Step)
Field | Description
Step Number | Sequential within phase (01, 02, 03…)
Task Title | e.g., "Final Term Sheet & Costing sheet in place"
Maker | Who is responsible - e.g., "Yubi & Issuer", "Issuer", "Legal Counsel"
Status | Pending / In Review / Done (checkbox or dropdown)
Sub-notes / Conditions | e.g., "≤1 yr (listed) / ≤6 mo (unlisted)" shown beneath task
Completion Toggle | Checkbox; ticking updates phase % and overall %

## Queries_Answers
PROJECT QUERIES & ANSWERS
Q# | Query | Answer / Status
Q1 | Complete Checklist Items | User requested compression to 3-5 items per phase. Critical items kept, rest moved to "Others" section (to be developed later). 📋 USER ACTION REQUIRED: Provide 3-5 key milestone items for each phase with: • Task Title • Maker/Responsible Party • Conditions/notes
Q2 | FS vs EF Checklist Differences | Main difference is FS (NBFC) regulated by RBI, requiring regulatory documents. Current approach: Keep it simple - not much difference. Examples from term sheet: • DOH (Deed of Hypothecation) for NBFC • Mortgage for Corporate
Q3 | Listed vs Unlisted Checklist Differences | Both Listed and Unlisted NCDs follow same checklist. Listed-only items (if any) will be marked during development. Examples: BSE SCORES registration, In-principle approval from BSE Exchange
Q4 | Deal Closure Workflow | All fields required before closing: • ISIN Number (mandatory) • Actual Coupon Rate • Actual Tenor in Months • Maturity Date (calculated or manual) • Final Rating (keep "Unrated" as option) Deal should be MOVED (deleted from Pipeline, added to Closed NCD Deal sheet)
Q5 | Fully Funded Status Definition | Option A selected: Separate checkbox/field "Funding Received" (Yes/No) Fully Funded status should automatically trigger deal closure workflow
Q6 | Term Sheet Template Customization | 1. Auto-select template sections: YES - based on FS/EF classification • FS (NBFC): DOH, Gold Loan Portfolio sections • EF (Corporate): Mortgage, DSCR sections 2. Pre-filled fields: • Issuer Name ✓ • Issuance Size/Quantum ✓ • T-Date ✓ • Listed/Unlisted status ✓ 3. Highlighting method: Option A - Cell background color (yellow, green, etc.)
Q7 | Document Storage | Phase 1: Local file system Path: E:\Personal\Trading_Champion\Projects\Solutions_Execution\Issuance Future (Phase 2): Google Drive API integration
Q8 | User Authentication & Roles | Phase 1: No user authentication - open access (single user/trusted team) Maker Tracking: Text field attribution (e.g., "Yubi & Issuer", "Issuer") Future (Phase 2): Maker/Checker/Admin roles
Q9 | Excel Update Mechanism | New Deals: Add to Pipeline Issuance sheet Existing Deals: Open, view, update checklist progress Data Flow: App maintains sync with Bond_Primary_Deals.xlsx using file-based read/write

## Data_Models
DATA MODELS & STRUCTURE
ISSUANCE PIPELINE (Sheet 1 in Bond_Primary_Deals.xlsx)
Field Name | Data Type | Notes / Validation
Sr. No. | Integer | Auto-incremented
Issuer | Text | Primary identifier - Required
Tentative Issuance Date | Date | T-date - Required
Listed/Unlisted | Dropdown | Listed ¦ Unlisted
Type | Dropdown | FS (Financial Sector/NBFC) ¦ EF (Enterprise Finance/Corporate)
Quantum (Cr.) | Number | In Crores - Required
Credit Clearance | Dropdown | Yes ¦ Pending ¦ On Hold ¦ Awaiting data from RM
Asset Class | Dropdown | MFI, NBFC, Housing Finance, Corporate, etc.
Assigned RM | Text | Optional
File/Folder Location | Text | Path to document folder
CLOSED NCD DEAL (Sheet 2 in Bond_Primary_Deals.xlsx)
Field Name | Data Type | Notes / Validation
Sr. No. | Integer | Auto-incremented
Issuer | Text | From Pipeline
Issue Date | Date | Actual T-date
ISIN | Text | Mandatory before closure
Coupon (XIRR) | Percentage | Actual coupon rate
Tenor (Months) | Integer | Actual tenor
Maturity Date | Date | Calculated or manual
Quantum (Cr.) | Number | Final amount
Rating | Text | Agency + rating (or "Unrated")
Listed/Unlisted | Dropdown | Listed ¦ Unlisted
FS/EF | Dropdown | FS ¦ EF - Added per user request

## Business_Rules_Forms
BUSINESS RULES & FORM FIELDS
BUSINESS RULES
Rule | Detail
Issuer Type | FS = NBFC/Financial Sector; EF = External Finance/Corporate Captured in Type field of Issuance Pipeline Added below Asset Class in Closed NCD sheet
Checklist Template | Listed NCD = full checklist Unlisted NCD = same checklist (per clarification) Template selected automatically at deal initiation
Deal Closure | When deal marked as Closed: • Removed from Pipeline view • Added to Closed NCD Deal sheet • Requires: ISIN, Coupon, Tenor, Maturity Date, Rating
Folder Storage | Files saved under respective company name folder: E:\Personal\Trading_Champion\Projects\Solutions_Execution\Issuance\[Company Name]
Credit Rating Validity | Listed: ≤1 year old Unlisted: ≤6 months old
T-Day Countdown Color | Red: ≤7 days Yellow: 8–21 days Green: >21 days
Progress Calculation | Formula: (completed steps / total steps for issuance type) × 100
Fully Funded Trigger | When "Funding Received" = Yes: • Automatically trigger deal closure workflow • Move to Closed NCD Deal sheet
NEW DEAL INITIATION FORM FIELDS
Field | Type & Validation
Issuer Name | Text input - Required Used as primary key across pipeline
Issuer Type | Dropdown - Required Options: FS / EF
Listed / Unlisted | Toggle / Radio - Required Determines checklist template
Quantum (Rs. Cr) | Number input - Required
Tentative Issuance Date (T) | Date picker - Required Drives countdown timer
Asset Class | Dropdown - Required Options: MFI, NBFC, Housing Finance, Corporate, etc.
Credit Clearance Status | Dropdown Options: Yes / Pending / On Hold / Data Pending
Assigned RM | Text / Dropdown - Optional
File / Folder Location | Text / URL - Optional Google Drive or folder path (manual entry)

## Task_vs_Achieved
NCD Tracker — Task vs Achieved ¦ Updated: 2026-03-14
# | Requirement / Task | Category | Priority | Status | Notes / Details | Completed On
1 | Fix ModuleNotFoundError — all subpackage imports (data., ui., utils., constants.) | Bug Fix | Critical | ✅ Done | Fixed across 7 files; all imports now use flat root-level names | 2026-03-14
2 | Connect Dashboard to actual Bond_Primary_Deals.xlsx (Pipeline Issuance sheet) | Data | Critical | ✅ Done | DataStore reads actual column names: Issuer, Quantum (Cr.), Listed/Unlisted, Type, etc. | 2026-03-14
3 | Connect Closed Deals tab to Closed NCD Deal sheet | Data | Critical | ✅ Done | DataStore maps Coupon (XIRR), Issue Date, FS/EF, etc. to model fields | 2026-03-14
4 | Handle partial date values ('Mar', 'Apr') → end-of-month 2026 dates | Data | High | ✅ Done | 'Mar' → 31/03/2026, 'Apr' → 30/04/2026 via parse_excel_date() | 2026-03-14
5 | Consolidate 15 Python files → 9 files | Architecture | Medium | ✅ Done | app, config, constants, models, utils, data_store, dashboard, deal_pages, term_sheet | 2026-03-14
6 | Add Issuer Type (FS/EF) field to pipeline model and new deal form | Feature | High | ✅ Done | PipelineDeal.issuer_type; dropdown added to New Issuance form | 2026-03-14
7 | Compact deal card UI matching reference image | UI | High | ✅ Done | Navy header, colored metric boxes, T-countdown pill, phase icons at bottom | 2026-03-14
8 | Term sheet generation button on Dashboard cards | Feature | High | ✅ Done | '📄 Term Sheet' button on each card generates draft .docx with available data | 2026-03-14
9 | Term sheet generation from Deal Detail page | Feature | High | ✅ Done | '📄 Draft Term Sheet' button in deal detail — downloads .docx | 2026-03-14
10 | Draft term sheet for Pipeline deals (no ISIN yet) | Feature | High | ✅ Done | generate_draft_for_pipeline() fills available fields; ISIN/coupon marked [TBD] | 2026-03-14
11 | Term sheet on deal closure → auto-populate + highlight manual fields | Feature | High | ✅ Done | Closure form generates final term sheet; unfilled placeholders highlighted yellow | 2026-03-14
12 | Issuance folder creation under E:\…\Issuance\[Company Name] | Feature | Medium | ✅ Done | create_company_folder() called on new deal creation and deal closure | 2026-03-14
13 | Copy Bond_Primary_Deals.xlsx into Code_Streamlit repo folder | Deployment | High | ✅ Done | File is now part of the GitHub repo; readable on Streamlit Cloud | 2026-03-14
14 | Copy Biz_Requirement_Streamlined.xlsx into Code_Streamlit repo folder | Deployment | Medium | ✅ Done | Available in repo for reference and updates | 2026-03-14
15 | Update config.py: cloud detection + DATA_FILE points to repo root | Config | High | ✅ Done | IS_CLOUD detects /mount/src; local uses __file__.parent for DATA_FILE | 2026-03-14
16 | Update requirements.txt with flexible version pins | Deployment | Medium | ✅ Done | >=1.31.0 etc. avoids dependency conflicts on Streamlit Cloud | 2026-03-14
17 | Push all fixes to GitHub (prabhuken01/ncd-tracker) | Deployment | High | ✅ Done | Force-pushed complete codebase; Streamlit Cloud auto-redeploys | 2026-03-14
18 | Google Sheets integration for persistent cloud storage | Phase 2 | High | ⏳ Pending | Requires service account JSON key; code structure ready for migration
19 | Streamlit Cloud deployment — verify app loads without errors | Deployment | Critical | ⏳ Pending | To be verified after GitHub push and Streamlit Cloud redeploy
20 | User authentication (Maker / Checker / Admin roles) | Phase 2 | Medium | ⏳ Phase 2 | Planned for Phase 2; no auth in Phase 1 (open access)
21 | Email / Slack notifications for T-day and overdue tasks | Phase 2 | Low | ⏳ Phase 2 | Planned for Phase 2
22 | ISIN auto-tracking with NSDL/CDSL | Phase 2 | Low | ⏳ Phase 2 | Planned for Phase 2